## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | Sign in with email and password | Accounts and access | Medium | FR-AUTH-01 (Report 3 §3.2.1) | Iteration 1 | Done
2 | Sign in with an FPT Google account | Accounts and access | Complex | FR-AUTH-02 (Report 3 §3.2.2) | Iteration 1 | Done
3 | Password reset, invitation and change | Accounts and access | Medium | FR-AUTH-03 (Report 3 §3.2.3) | Iteration 1 | Done
4 | Student account verification | Accounts and access | Complex | FR-AUTH-04 (Report 3 §3.2.4) | Iteration 1 | Done
5 | Import the student list | Accounts and access | Complex | FR-AUTH-05 (Report 3 §3.2.5) | Iteration 1 | Done
6 | Users, roles and permissions | Accounts and access | Medium | FR-AUTH-06 (Report 3 §3.2.6) | Iteration 1 | Done
7 | Staff accounts and workload | Accounts and access | Medium | FR-AUTH-07 (Report 3 §3.2.7) | Iteration 1 | Done
8 | Reconcile the enrolled list | Accounts and access | Complex | FR-AUTH-08 (Report 3 §3.2.8) | Iteration 1 | Done
9 | Audit Log and student directory | Accounts and access | Simple | FR-AUTH-09 (Report 3 §3.2.9) | Iteration 1 | Done
10 | Room Types, Room Classes and default prices | Registration periods and configuration | Medium | FR-CFG-01 (Report 3 §3.3.1) | Iteration 1 | Done
11 | Utility prices and Utility Deposit | Registration periods and configuration | Simple | FR-CFG-02 (Report 3 §3.3.2) | Iteration 1 | Done
12 | Rules: eligibility, priority, matching, deadlines, refunds, stay | Registration periods and configuration | Complex | FR-CFG-03 (Report 3 §3.3.3) | Iteration 1 | Done
13 | Registration-period requests | Registration periods and configuration | Medium | FR-CFG-04 (Report 3 §3.3.4) | Iteration 1 | Done
14 | Build and publish a Term | Registration periods and configuration | Complex | FR-CFG-05 (Report 3 §3.3.5) | Iteration 1 | Done
15 | Block settings | Registration periods and configuration | Medium | FR-CFG-06 (Report 3 §3.3.6) | Iteration 1 | Done
16 | System parameters and notification texts | Registration periods and configuration | Simple | FR-CFG-07 (Report 3 §3.3.7) | Iteration 1 | Done
17 | Demo data reset | Registration periods and configuration | Medium | FR-CFG-08 (Report 3 §3.3.8) | Iteration 1 | Done
18 | Blocks, Floors, Rooms and Beds | Inventory | Medium | FR-INV-01 (Report 3 §3.4.1) | Iteration 1 | Done
19 | Room Class per Room per Term | Inventory | Medium | FR-INV-02 (Report 3 §3.4.2) | Iteration 1 | Done
20 | Furniture types, items and QR labels | Inventory | Medium | FR-INV-03 (Report 3 §3.4.3) | Iteration 1 | Done
21 | Door codes | Inventory | Complex | FR-INV-04 (Report 3 §3.4.4) | Iteration 1 | Done
22 | Room hub | Inventory | Simple | FR-INV-05 (Report 3 §3.4.5) | Iteration 1 | Done
23 | Term and eligibility | Applications | Medium | FR-APP-01 (Report 3 §3.5.1) | Iteration 1 | Done
24 | Application wizard and Deposit Invoice | Applications | Complex | FR-APP-02 (Report 3 §3.5.2) | Iteration 1 | Done
25 | Roommate invitation | Applications | Medium | FR-APP-03 (Report 3 §3.5.3) | Iteration 1 | Done
26 | Cancel and expire an Application | Applications | Simple | FR-APP-04 (Report 3 §3.5.4) | Iteration 1 | Done
27 | Review Applications | Applications | Medium | FR-APP-05 (Report 3 §3.5.5) | Iteration 1 | Done
28 | My Applications | Applications | Simple | FR-APP-06 (Report 3 §3.5.6) | Iteration 1 | Done
29 | Round 2 | Applications | Medium | FR-APP-07 (Report 3 §3.5.7) | Iteration 1 | Done
30 | Assignment run | Assignment, residence, Term transition | Complex | FR-ASG-01 (Report 3 §3.6.1) | Iteration 1 | Done
31 | Resolve conflicts | Assignment, residence, Term transition | Medium | FR-ASG-02 (Report 3 §3.6.2) | Iteration 1 | Done
32 | Approve the assignment and issue Balances | Assignment, residence, Term transition | Complex | FR-ASG-03 (Report 3 §3.6.3) | Iteration 1 | Done
33 | Check-in, door code release and My Room | Assignment, residence, Term transition | Complex | FR-ASG-04 (Report 3 §3.6.4) | Iteration 1 | Done
34 | Late check-in | Assignment, residence, Term transition | Medium | FR-ASG-05 (Report 3 §3.6.5) | Iteration 1 | Done
35 | Check-out and settlement | Assignment, residence, Term transition | Complex | FR-ASG-06 (Report 3 §3.6.6) | Iteration 1 | Done
36 | Requests window (M2, M3) | Assignment, residence, Term transition | Complex | FR-ASG-07 (Report 3 §3.6.7) | Iteration 1 | Done
37 | Next-Term fees (M6, M7) | Assignment, residence, Term transition | Complex | FR-ASG-08 (Report 3 §3.6.8) | Iteration 1 | Done
38 | Terminations | Assignment, residence, Term transition | Medium | FR-ASG-09 (Report 3 §3.6.9) | Iteration 1 | Done
39 | Operational moves and turnover | Assignment, residence, Term transition | Complex | FR-ASG-10 (Report 3 §3.6.10) | Iteration 1 | Done
40 | Balance forfeit | Assignment, residence, Term transition | Medium | FR-ASG-11 (Report 3 §3.6.11) | Iteration 1 | Done
41 | Invoices and the VietQR payment page | Payments and billing | Medium | FR-BIL-01 (Report 3 §3.7.1) | Iteration 1 | Done
42 | Claim a transfer | Payments and billing | Medium | FR-BIL-02 (Report 3 §3.7.2) | Iteration 1 | Done
43 | Confirm or reject payment claims | Payments and billing | Complex | FR-BIL-03 (Report 3 §3.7.3) | Iteration 1 | Done
44 | Meter readings and Utility Invoices | Payments and billing | Complex | FR-BIL-04 (Report 3 §3.7.4) | Iteration 1 | Done
45 | Overdue Invoices and Utility debt | Payments and billing | Complex | FR-BIL-05 (Report 3 §3.7.5) | Iteration 1 | Done
46 | Refunds | Payments and billing | Medium | FR-BIL-06 (Report 3 §3.7.6) | Iteration 1 | Done
47 | Payment reminders and collections | Payments and billing | Medium | FR-BIL-07 (Report 3 §3.7.7) | Iteration 1 | Done
48 | Next-Term room change | Next-Term requests, routing, time limits | Medium | FR-REQ-01 (Report 3 §3.8.1) | Iteration 1 | Done
49 | Swap of next-Term Beds | Next-Term requests, routing, time limits | Complex | FR-REQ-02 (Report 3 §3.8.2) | Iteration 1 | Done
50 | Room Class change of a Room | Next-Term requests, routing, time limits | Complex | FR-REQ-03 (Report 3 §3.8.3) | Iteration 1 | Done
51 | Extension and end of stay | Next-Term requests, routing, time limits | Medium | FR-REQ-04 (Report 3 §3.8.4) | Iteration 1 | Done
52 | Decide next-Term requests | Next-Term requests, routing, time limits | Complex | FR-REQ-05 (Report 3 §3.8.5) | Iteration 1 | Done
53 | Routing rules and time limits | Next-Term requests, routing, time limits | Medium | FR-REQ-06 (Report 3 §3.8.6) | Iteration 1 | Done
54 | Overdue requests (escalations) | Next-Term requests, routing, time limits | Complex | FR-REQ-07 (Report 3 §3.8.7) | Iteration 1 | Done
55 | Report a Maintenance Request | Maintenance and inspections | Medium | FR-MNT-01 (Report 3 §3.9.1) | Iteration 1 | Done
56 | Handle Maintenance Requests | Maintenance and inspections | Medium | FR-MNT-02 (Report 3 §3.9.2) | Iteration 1 | Done
57 | Inspection checklists | Maintenance and inspections | Medium | FR-MNT-03 (Report 3 §3.9.3) | Iteration 1 | Done
58 | Inspection schedules and runs | Maintenance and inspections | Complex | FR-MNT-04 (Report 3 §3.9.4) | Iteration 1 | Done
59 | In-app notifications | Notifications | Simple | FR-NTF-01 (Report 3 §3.10.1) | Iteration 1 | Done
60 | Push and email | Notifications | Complex | FR-NTF-02 (Report 3 §3.10.2) | Iteration 1 | Done
61 | Announcements and the dormitory board | Notifications | Medium | FR-NTF-03 (Report 3 §3.10.3) | Iteration 1 | Done
62 | Notification templates | Notifications | Medium | FR-NTF-04 (Report 3 §3.10.4) | Iteration 1 | Done
63 | Send emails to student groups | Notifications | Medium | FR-NTF-05 (Report 3 §3.10.5) | Iteration 1 | Done
64 | Dashboards per role | Reports | Medium | FR-RPT-01 (Report 3 §3.11.1) | Iteration 1 | Done
65 | Term dashboard and reports | Reports | Complex | FR-RPT-02 (Report 3 §3.11.2) | Iteration 1 | Done
66 | CSV export | Reports | Medium | FR-RPT-03 (Report 3 §3.11.3) | Iteration 1 | Done
67 | Search | Reports | Simple | FR-RPT-04 (Report 3 §3.11.4) | Iteration 1 | Done
68 | Student app | Android app | Complex | FR-MOB-01 (Report 3 §3.12.1) | Iteration 1 | Done
69 | End-to-end workflow tests WF-01..05 on staging | Testing | Complex | TC-WF-01..05, demo scenarios DS-01..10 | Iteration 2 | Pending
70 | Automation of the workflow tests in CI | Testing | Complex | API scenario tests (gap G2) | Iteration 2 | Pending
71 | Load test NFR-01, uptime monitor NFR-04, deployment times NFR-06 | Testing | Medium | TC-NFR-01, 04, 06 (gap G3) | Iteration 2 | Pending
72 | Concurrency test one Allocation per Bed per Term | Testing | Medium | TC-NFR-03 (gap G4) | Iteration 2 | Pending
73 | Android UI tests (sign-in, payment claim, door code) | Android app | Medium | Gap G5 | Iteration 2 | Pending
74 | Fixes from Review 2 and the self-review (BM02 Planned items) | All | Medium | Review 2 Commitment (BM04) | Iteration 2 | Pending
75 | Report 6 User Guides, updated Reports 1–5, Full Software Package | Documents | Medium | Before Defense 1.1 | Iteration 3 | Pending
76 | Report 7, defense slides, final package | Documents | Medium | Final defense | Iteration 3 | Pending

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Review 1: the Tân Uyên dormitory is not operating; what is the basis of the design? | Requirements may not fit real operation | High | Lê Thành Minh Trung | 30/09/2026 | 27/10/2026 | Closed | Basis stated in Report 1 §2 and the registration form 2.0: FPT dormitories, Circular 27/2011, VNU-HCM, configurable rules
2 | Review 1: what makes the solution practical? | Scope credibility | High | Lê Thành Minh Trung | 30/09/2026 | 27/10/2026 | Closed | Production deployment with demo stages; configurable rules; Report 1 §5
3 | Review 1: identify the current operation of the Tân Uyên dormitory to derive requirements | Requirements | High | Lê Thành Minh Trung | 30/09/2026 | 27/10/2026 | Closed | Workflows WF-01..05 and business rules (Report 3 §5.1), assumptions listed
4 | Review 1: add the Manager role (general management, reports, statistics, Block management) | Actors, permissions, screens | High | Lê Thành Minh Trung | 30/09/2026 | 24/10/2026 | Closed | Change Specification v2 phase 1–2; Manager portal
5 | No bank API or payment-gateway contract for automatic payment matching | Payments cannot be confirmed automatically | High | Lê Thành Minh Trung | 20/10/2026 | 26/10/2026 | Closed | ADR-22: claims confirmed by Managers (v2 phase 5)
6 | Members other than the leader have written little of Iteration 1 code (bus factor) | Ownership verification at Review 2 and Defense 1.1 | High | Lê Thành Minh Trung | 27/10/2026 |  | Open | Ownership map, training plan (Report 2 §2.3); each member changes their part before Defense 1.1
7 | End-to-end workflow tests and NFR measurements not done yet | Defense 1.1 thresholds | Medium | Võ Minh Luân | 28/10/2026 |  | Open | Iteration 2 (sprints S5–S6)
8 | Defense 1.1 and final defense dates not announced | Planning of Iteration 2–3 | Medium | Lê Thành Minh Trung | 28/10/2026 |  | Open | Ask the department; plan assumes Defense 1.1 mid-December
9 | Azure for Students credit and the free database period | Production could stop before the final defense | Medium | Lê Thành Minh Trung | 23/10/2026 |  | Open | Budget alert $5/month; runbook for another VPS

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Reports | Dashboards (all roles) | Lê Thành Minh Trung | Dashboards failed before the first Term existed | Lê Thành Minh Trung | Closed | fix(rpt) 22/10/2026; regression TC-RPT-011
Reports | Occupancy, finance reports | Lê Thành Minh Trung | Past Terms lost their reports; refunds without a Bed were not counted by gender | Lê Thành Minh Trung | Closed | fix(rpt) 22/10/2026; TC-RPT-010
DevOps | Deploy job | Lê Thành Minh Trung | A deploy key pasted with Windows line ends broke the SSH deploy | Lê Thành Minh Trung | Closed | fix(deploy) 24/10/2026
Web | Vercel production build | Lê Thành Minh Trung | Production deployments on Vercel were skipped when only backend files changed | Trần Võ Quang Duy | Closed | fix(web) 24/10/2026
Accounts | Startup | Lê Thành Minh Trung | Spring created a default user and printed its password in the log | Lê Thành Minh Trung | Closed | fix(auth) 24/10/2026; TC-AUTH-028
Accounts | Admin setup checks, texts | Lê Thành Minh Trung | Texts still named "the Block Manager"; the setup check did not ask for Staff per Block | Lê Thành Minh Trung | Closed | fix(auth) 24/10/2026
Accounts | Sign in with Google (web) | Lê Thành Minh Trung | Google sign-in failed when the browser blocked the popup | Lê Thành Minh Trung | Closed | fix(auth) 25/10/2026; TC-AUTH-051, 052
Web | Student Home | Lê Thành Minh Trung | Student Home did not scroll; the Term timeline wrapped | Trần Võ Quang Duy | Closed | fix(web) 27/10/2026
Web | Back-office search, sidebar | Lê Thành Minh Trung | Search label wrapped; sidebar labels cut | Trần Võ Quang Duy | Closed | fix(web) 27/10/2026
Registration periods | Term wizard, Rooms and places step | Lê Thành Minh Trung | Places row misaligned; excluded Rooms typed by hand only | Trần Võ Quang Duy | Closed | feat(web) 27/10/2026: import from Excel/CSV; TC-INV-025
Billing | Utility debt job | Lê Thành Minh Trung | The final warning could be issued again for the same debt | Lê Thành Minh Trung | Closed | Fixed with the demo tool 27/10/2026
Documents | SDD state machines | Lê Thành Minh Trung | Application, Allocation and Invoice state machines missed transitions used in code | Lê Thành Minh Trung | Closed | Report 4 §3.1 redrawn from the code 28/10/2026
Documents | Backend architecture note | Lê Thành Minh Trung | Architecture note still named Flutter for the Android app | Võ Minh Luân | Closed | docs 28/10/2026

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
30/09/2026 | How can a dormitory that does not operate yet be specified? | Review 1 council | High | Closed | Use FPT's operating dormitories, regulations and comparable systems; keep rules configurable (Report 1 §2)
30/09/2026 | Which roles are needed? | Review 1 council | High | Closed | Add the Manager (general management, reports, Block management)
20/10/2026 | Is the scope of the API contract and UI confirmed? | Team → mentor | High | Closed | Confirmed by the mentor (ADR-12)
24/10/2026 | May payments be confirmed by Managers instead of a bank integration? | Team → mentor | High | Closed | Yes; no bank contract is available (ADR-22)
28/10/2026 | May the production server serve as the staging (demo) environment for Defense 1.1? | Team → reviewers | Medium | Open | Proposed in Report 4 §1.3.4; to confirm at Review 2
28/10/2026 | Is the NFR-01 load test on a local server with the production configuration accepted? | Team → reviewers | Medium | Open | Proposed in the Design Brief §7; to confirm at Review 2
28/10/2026 | Dates of Defense 1.1 and the final defense? | Team → department | Medium | Open